## Hoja1
		OC FOSS Policy - PLAN

Abbreviations
	FOSS Team	team established for setting up and implementing this plan
	FOSS	Free and Open Source Software
	FCO	FOSS Compliance Officer
	OSRB	Open Source Review Board
	FPO	FOSS Project Office	at start, same as OSRB
	FCA	FOSS Compliance Artefacts	generally, Review Report, Licenses, Source Code
	OpenChain	Specification established for ensuring FOSS Compliance
	FOSS Liaison	person designated to deal with outside enquiries	Generallly = FCO

		TO DO	DOING	DONE

1	Situation Analysis
			Appoint FOSS Project Team	review Project 1 FOSS usage
				Analyse Project 1 FOSS usage
			review Project 1 contracts
			Review Project 1 Processes
			request info from SWI
				Draft Project Plan
				Confirm Project Plan
		Draft Situation Report and Recommendation
		Share Report and Recommendations with FOSS Team
		Carry out OC conformance check
			Identify Project 2

2	Definition of Policy and Procedures
	Policy		Draft Policy
			Determine Policy Owner and Team
			Review FOSS Policy by FOSS Team
		Approve FOSS Policy at FOSS Team level
		Approve FOSS Policy at Steering level
		Store Policy

		Define FOSS Contribution Policy

	Procedures		Identify FOSS Review Procedures
		Define FOSS Identification Procedure
			Define FOSS License Collection Procedure
			Define FOSS Tracking procedure
			Define FOSS obligations Review Procedure
			Define FOSS use case and obligations analysis process
			Define FOSS source code management process
			Define FOSS non-conformity handling process
		Define Supply Chain Contract identification, analysis and storage process
		Define FOSS Distribution (delivery) compliance process
			Define FOSS FCA Archiving process
			Define FOSS FCA retrieval process
		Define FOSS Contribution process

		Define FOSS Policy Review and Update Process
		Define FOSS Review Procedure Review and Update Processs

			Define FOSS Compliance Audit process
		Integrate FOSS Procedures in Quality stream
		Review Procedures by FOSS Team

		Define FOSS Liaison protocol
		Define FOSS Tools manager
	Tools		Draft FOSS Review Templates
		Determine FOSS Compliance Tools
		Determine FCA Repository

3	Implementation
	Roles		Designate FCO
			Designate OSRB
			Designate FPO
			Designate FOSS Liaison
		Set up FOSS Liaison communication channels
		Designate FOSS Steering Committee

	Training	Adapt OpenChain curriculum to Company
		Plan Team and Staff Training
		FCO and FPO Training
		Tech and Quality and Legal Staff Training
		Train FOSS Liaison
		Train Tech Staff on FOSS Compliance Tools

	Procedures	Quality to determine FOSS procedure implementation Plan
		Distribute FOSS Procedure Templates

	Tools	Set up FOSS Policy and Documentation repository
		Set up FCA repository
		Set up FOSS compliance Tools

4	Communication
		Determine Communication Content
		Detemermine Communication Channel
		Communicate FOSS Policy to Company
		Communicate FOSS Policy external

5	Certification
		OpenChain self certification
		Notify OpenChain self certification